## Tracker
workstream | deliverable | status | duration | startDate | endDate | progress | phase | milestone | owner
Benefits | Benefits Alignment | WIP | 5 | 2025-12-15 | 2025-12-22 | 10 | Design | Ready to Source | Binoy Mohanty
Benefits | Insurance Premium Payment | Delayed | 5 | 2026-01-06 | 2026-01-13 | 20 | Design | Ready to Onboard | Binoy Mohanty
Compensation | Finalize Career Architecture, Comp Structure and Salary Ranges | Closed | 7 | 2025-12-17 | 2025-12-26 | 30 | Design | Ready to Source | Binoy Mohanty
EUC and IT | EUC and Networking Specifications | Closed | 4 | 2025-12-15 | 2025-12-19 | 40 | Intake | Ready to Onboard | Jon Conticello
Finance | Bank Selection | Closed | 2 | 2025-12-15 | 2025-12-17 | 10 | Intake | Ready to Source | Thom Balding
Finance | Financial Modelling and Forecasting for expense management | Closed | 5 | 2025-12-29 | 2026-01-05 | 20 | Design | Ready to Source | Thom Balding
HR Policies | Critical HR Policies | Delayed | 4 | 2025-12-15 | 2025-12-19 | 30 | Design | Ready to Source | Asha Bhandary
Legal | Entity Type & Name selection | WIP | 2 | 2025-12-12 | 2025-12-16 | 40 | Design | Ready to Source | Justin
Legal | Name Reservation Application and Approval by MCA | Blocked | 4 | 2025-12-23 | 2025-12-29 | 30 | Design | Ready to Source | Sidharth Iyer
Legal | Preparation & Filing of COI (Need Workspace finalized) | WIP | 3 | 2025-12-30 | 2026-01-02 | 40 | Design | Ready to Source | Sidharth Iyer
Legal | Board Meeting post COI for applying for Bank A/C and auditor appointment | Yet to Start | 3 | 2026-01-15 | 2026-01-20 | 20 | Design | Ready to Onboard | Sidharth Iyer
Talent Acquisition | India Hiring Demand and Job Descriptions | Yet to Start | 4 | 2025-12-10 | 2025-12-16 | 30 | Intake | Ready to Source | Kellie Green
Compensation | EVP and Pay Philosophy | Blocked | 2 | 2025-12-10 | 2025-12-12 | 40 | Intake | Ready to Source | Kellie Green
Employer Branding | Brand Guidelines | WIP | 2 | 2025-12-10 | 2025-12-12 | 10 | Intake | Ready to Source | Kellie Green
Systems | HRIS and Payroll System Design | On Hold | 5 | 2025-12-12 | 2025-12-19 | 20 | Intake | Ready to Source | Kellie / John
Talent Acquisition | Hiring in India' Manager Readiness workshop | WIP | 3 | 2025-12-23 | 2025-12-26 | 30 | Design | Ready to Source | Amrita Thaper
Workspace | Location Finalization | WIP | 5 | 2025-12-15 | 2025-12-22 | 10 | Design | Ready to Source | Justin
Workspace | Workspace Design + Branding | WIP | 10 | 2026-01-02 | 2026-01-16 | 20 | Design | Ready to Onboard | Justin / Ranjit
Benefits | Insurance (GMC and GPA) payments | WIP | 2 | 2026-02-09 | 2026-02-11 | 30 | Setup | Ready to Onboard | Binoy Mohanty
Employer Branding | Swag Kits Delivery | WIP | 21 | 2026-01-15 | 2026-02-13 | 30 | Setup | Ready to Onboard | Shoma Majumdar
EUC and IT | Physical IT Assets | WIP | 15 | 2026-01-15 | 2026-02-05 | 40 | Setup | Ready to Onboard | Siva Teja
Finance | Bank A/C application and activation | On Hold | 5 | 2026-01-21 | 2026-01-28 | 10 | Setup | Ready to Onboard | Vivek Jhanwar
Finance | Capital Infusion by ANSR for transacting with India Bank A/C | WIP | 3 | 2026-02-03 | 2026-02-06 | 20 | Setup | Ready to Onboard | Vivek Jhanwar
Finance | GST Registration with IT Dept for vendor contracting and payments | WIP | 15 | 2026-01-21 | 2026-02-11 | 30 | Setup | Ready to Onboard | Rohit Lal
Legal | Receipt of Commencement of Business Certificate | WIP | 2 | 2026-02-13 | 2026-02-17 | 40 | Setup | Ready to Onboard | Sidharth Iyer
Legal | Receipt of Certificate of Incorporation (COI) | WIP | 7 | 2026-01-05 | 2026-01-14 | 10 | Setup | Ready to Offer | Sidharth Iyer
Org Design | Design Playbook | WIP | 7 | 2025-12-29 | 2026-01-07 | 20 | Design | Ready to Offer | Harish
Systems | HRIS and Payroll System - Setup | WIP | 5 | 2026-01-23 | 2026-01-30 | 30 | Setup | Ready to offer | Arun Soman
Talent Acquisition | Post Jobs in ATS | WIP | 2 | 2026-01-08 | 2026-01-12 | 5 | Setup | Ready to Source | Amrita Thaper

## Status
WIP
Closed
On Hold
Delayed
Blocked
Yet to Start
PO Raised
RFI Awaited